# D365 F&O Analytics Migration — Resource Estimate v3.0

Resource, Effort & Delivery Plan — Phases 1 through 5

Table of Contents

# D365 F&O Analytics Migration — Enterprise Program Estimate

Resource, Effort & Delivery Plan — Phases 1 through 5

| Attribute | Detail |
| --- | --- |
| Source system | Microsoft Dynamics AX 2012 |
| Target system | Microsoft Dynamics 365 Finance & Operations |
| Analytics platform | Azure Databricks (Unity Catalog, Delta Lake) |
| Ingestion | Azure Databricks Lakeflow Connect D365 connector reading from ADLS Gen2 (Synapse Link output, delivered by separate team) |
| Accelerators | AI development agent + Microsoft FastTrack Implementation Assets |
| Scope of estimate | Phases 1–5 (Business Insight Review, Raw & Silver, Dimensional Model, OBT, Insight Implementation) |
| Timeline | 6 weeks (Phase 1) + 9 months (Phases 2–5) = ~10.5 months total |
| Scale of scope | 12,000 insight questionnaires · ~200 D365 F&O entities · ~50 dims · ~30 facts · ~30 OBTs |
| Document version | 3.0 — Accelerator-adjusted release; supersedes v2.0 (July 2026 baseline) |
| Prepared | July 2026 |

# 1. Executive Summary

This document estimates the resources, effort, and delivery approach required to migrate the analytics platform from Microsoft Dynamics AX 2012 to Microsoft Dynamics 365 Finance & Operations on Azure Databricks, using three accelerators applied against the v2.0 baseline: an AI development agent, the Microsoft FastTrack Implementation Assets, and the Azure Databricks Lakeflow Connect D365 connector consuming Azure Synapse Link output from ADLS Gen2.

The program is delivered in two consecutive workstreams: Phase 1 (Business Insight Review) over 6 weeks, followed by Phases 2–5 (implementation) over 9 months.

## Headline Numbers — Verified

| Metric | Baseline (v2.0) | With Accelerators (v3.0) | Reduction |
| --- | --- | --- | --- |
| Total program effort | ~47,036 person-hours | ~29,200–31,500 person-hours | ~33–38% |
| Person-months | ~310 | ~192–207 | ~33–38% |
| Phase 1 effort (6 weeks) | ~7,500 hrs / 36 reviewers | ~6,300–6,700 hrs / 30–32 reviewers | ~11–16% |
| Phases 2–5 effort (9 months) | ~38,800 hrs | ~19,900–22,000 hrs | ~43–49% |
| Peak team size (Phases 2–5, M5–M7) | 45 FTEs | ~29–32 FTEs | ~29–36% |
| Peak team size (Phase 1, Weeks 1–6) | 40 FTEs | ~35–37 FTEs | ~8–13% |
| Total program duration | ~10.5 months | ~10.5 months (unchanged) | Timeline preserved |
| Includes 10% contingency | Yes | Yes | — |
| Delivery confidence at v3.0 estimate | Moderate–High, contingent on Phase 1 questionnaire quality, AI priming quality, and business-user availability across both phases |  |  |

## Primary Delivery Risk

Phase 5 remains the dominant workstream (~40% of accelerator-adjusted program effort) and requires implementation of ~12,000 business insights across ~4.5 months of active development. With AI-assisted pattern-based development against cleanly-structured OBTs, the required throughput of approximately 130 insights/day is achievable with ~10–12 data engineers rather than the 20 in the baseline. The dominant risks shift from staffing volume to accelerator effectiveness:

- Phase 1 questionnaire quality — upstream gate for AI-assisted Phase 5 code generation

- AI agent priming quality — a generic AI model without F&O context delivers materially less than a domain-primed one

If either is weak, the accelerator savings collapse and the program reverts toward the baseline estimate.

# 2. Accelerator Context

## 2.1 Azure Databricks D365 Connector

The Lakeflow Connect Dynamics 365 connector reads Synapse Link changelogs directly from ADLS Gen2 (populated by a separate team) and creates streaming tables in Unity Catalog. Impact:

- Eliminates most Bronze layer engineering (auto-discovers schema, creates streaming tables, handles incremental via versionnumber, maps Dataverse types to Delta types, manages CRUD from Dataverse)

- Retained constraints: 250-tables-per-pipeline limit still requires 2–3 domain-oriented pipeline designs; no automated schema evolution (schema-drift monitoring still required); option-set integers, GUID lookups, and multi-select fields still require Silver-layer decoding

## 2.2 Microsoft FastTrack Implementation Assets

The Dynamics 365 FastTrack team maintains a repository (microsoft/Dynamics-365-FastTrack-Implementation-Assets) of F&O analytics patterns. Directly relevant to this program:

| Asset | Where it helps |
| --- | --- |
| CDMUtil parsing patterns | Silver layer entity metadata handling |
| Entity list templates (EntityList.json) | Domain-oriented pipeline design |
| Sub-table / super-table map | Avoids re-discovery of F&O sub-tables (CompanyInfo, DirPerson etc.) |
| Enum translation logic | Silver-layer option-set integer decoding |
| remove_mserp_prefix pattern | F&O virtual entity naming |
| View syntax replacement | SQL view syntax handling |
| Architecture patterns | Reference medallion patterns for F&O |

Important: FastTrack assets are Synapse-oriented; porting to Databricks/PySpark is real engineering work, included in the Phase 2 estimate.

## 2.3 AI Development Agent

An AI agent capable of generating Delta Lake DDL, PySpark/Spark SQL transformations, SCD merge logic, DQ expectations, unit test scaffolding, and documentation from structured specifications. The AI does not replace human judgment for design decisions, domain interpretation, business rule verification, or business-user interaction. New activity introduced by AI adoption: agent priming with F&O entity model, dimensional model, OBT schemas, and questionnaires — estimated at 200–400 hours in Months 4–5.

# 3. Solution Architecture on Azure Databricks

All layers are implemented on the Azure Databricks platform, using Delta Lake as the storage format and Unity Catalog for governance.

## 3.1 Ingestion Path (Simplified by D365 Connector)

F&O data is replicated to ADLS Gen2 via Azure Synapse Link (managed by a separate team). Databricks then ingests directly using the Lakeflow Connect Dynamics 365 connector which reads Synapse Link changelogs and creates streaming tables in Unity Catalog. This eliminates the custom Bronze pipeline engineering that would otherwise be required.

## 3.2 Medallion Layers

| Layer | Purpose | Databricks Implementation | Accelerator |
| --- | --- | --- | --- |
| Bronze / Raw | Immutable landing of source data | Delta streaming tables auto-created by Lakeflow Connect connector; partitioned by ingest date | D365 Connector |
| Silver | Cleansed, standardized, deduplicated, conformed; option-sets decoded, GUID lookups resolved, SCD applied | Delta tables built via Databricks pipelines with FastTrack CDM patterns and AI-generated transformations | FastTrack + AI |
| Gold — Dimensional Model | Enterprise Kimball star schema | Delta tables managed by Unity Catalog; primary key/foreign key hints; liquid clustering | AI code gen for dim/fact scaffolding |
| Gold — OBT | Denormalized wide tables per analytical domain | Delta tables with liquid clustering; incremental MERGE | AI join scaffolding |
| Insight Layer | Business calculations, metrics, and views serving ~12,000 documented insights | Delta tables and views on top of OBTs; AI-generated SQL/PySpark expressions matching approved business rules | AI insight generation |

## 3.3 Governance & Operations

Unity Catalog for centralized governance, lineage, column-level security. Delta Live Tables or Databricks Workflows for orchestration. Great Expectations or built-in DLT expectations for DQ. Databricks Asset Bundles integrated with Azure DevOps or GitHub Actions for CI/CD. Photon runtime enabled on analytical clusters. Custom schema-drift monitoring for the D365 connector.

# 4. Scope Baseline and Sizing Assumptions

The scope is unchanged from the baseline. Assumptions:

| Object type | Estimated count | Sizing basis |
| --- | --- | --- |
| D365 F&O entities / tables to ingest | ~200 | Derived from 500 SQL views, 100 dataflows, 750 reports across all domains |
| Dimension tables (Gold) | ~50 | Standard ERP dimensional model |
| Fact tables (Gold) | ~30 | GL, AP, AR, POs, SOs, inventory movements, etc. |
| One Big Tables (OBT) | ~30 | One primary OBT per major analytical domain |
| Business insights | 12,000 | Given: 750 reports × 4 pages × 4 insights |
| Business domains | ~10 | Finance, AP, AR, FA, Inventory, Procurement, Sales, Production, HR, Cross-functional |

Recommended First Action: A 2-week discovery spike in Weeks 1–2 should validate these counts against the actual environment. Divergence of more than 20% on entity count or insight complexity distribution warrants a re-baselining of the estimates in Sections 5 through 9 before final staffing commitments are made.

# 5. Phase 1 — Business Insight Review

Phase 1 is the data-engineering review of the 12,000 completed business insight questionnaires. Data engineers read all 24 answers per insight to genuinely understand each one, call business users where clarification is required, and mark questionnaires ready for Phase 2.

## 5.1 Scope

- Read and understand each business insight in the context of the source report

- Review all 24 questionnaire responses per insight for completeness, consistency, and clarity

- Identify missing, ambiguous, or conflicting information

- Schedule and conduct clarification discussions with the relevant business users where required

- Update questionnaires with the agreed clarifications and mark them as ready for technical analysis

## 5.2 Where the Accelerators Apply

AI agent contribution (limited): - Duplicate insight detection across the 12,000 corpus (estimated 10–15% duplicate rate → 1,200–1,800 insights eliminated from workload) - Completeness check — auto-flag missing or contradictory answers - Structured summarisation to speed engineer reading

FastTrack and D365 Connector: not applicable — this phase is business questionnaire review; F&O metadata assets and Bronze connectors do not apply.

## 5.3 Estimation Model

| Parameter | Optimistic | Realistic (v3) | Conservative |
| --- | --- | --- | --- |
| Base review time per insight (with AI assist) | 15 min | 25 min | 40 min |
| % of insights requiring discussion | 12% | 22% | 38% |
| Average discussion duration | 20 min | 30 min | 45 min |
| Effective time per insight | 17.4 min | 31.6 min | 57 min |
| Total effort (12,000 insights) | 3,500 hrs | 6,300–6,700 hrs | 11,400 hrs |
| Engineers required (6 weeks × 5 days × 7 hrs = 210 hrs each) | 17 | 30–32 | 54 |

## 5.4 Realistic Effort Breakdown

| Component | Basis | Hours |
| --- | --- | --- |
| Base questionnaire review (AI-assisted) | 12,000 × 25 min | 5,000–5,300 |
| Business-user discussions (contribution) | 12,000 × 22% × 30 min | 1,300–1,400 |
| Phase 1 Total (realistic) |  | 6,300–6,700 |

Person-days: 900–957 · Person-months: 41–44

## 5.5 Phase 1 Team Composition

| Role | Count | Responsibilities |
| --- | --- | --- |
| Data Engineer (Reviewer) | 30–32 | Read and validate questionnaires; flag issues; conduct clarification discussions; update questionnaires |
| Business Analyst | 2 | Coordinate business user discussions; track review progress; escalate ambiguity patterns |
| D365 F&O Functional Consultant | 1 | Domain support for business-rule interpretation across ERP modules |
| Project Manager | 1 | Delivery coordination, business-user scheduling, weekly progress reporting |
| Solution Architect (part-time) | 1 | Consistency oversight to ensure review outputs are usable inputs for Phases 2–5 |
| Phase 1 subtotal | ~35–37 |  |

## 5.6 Continuity into Phases 2–5

A portion of the Phase 1 reviewer cohort — typically the strongest 8–10 engineers — should transition into Phase 2/3 as senior data engineers and BAs, carrying forward direct familiarity with the questionnaire content and business context.

# 6. Phase 2 — Raw and Silver Data Layer

## 6.1 Scope

- Identify required D365 F&O entities based on legacy AX 2012 SQL views, dataflows, and report requirements

- Configure the Lakeflow Connect D365 connector against ADLS Gen2 (Synapse Link output) — this replaces custom Bronze pipeline development

- Design 2–3 domain-oriented ingestion pipelines (respecting the 250-tables-per-pipeline limit)

- Build the Silver layer with cleansing, type resolution, option-set decoding, lookup GUID resolution, deduplication, business-key resolution, SCD handling, and data-quality enforcement — using FastTrack patterns as the framework and AI-generated per-entity code

- Validate row-count, sum-total, and business-key reconciliation against the AX 2012 source

## 6.2 Where the Accelerators Apply

D365 Connector: Eliminates most Bronze layer work — auto-creates streaming tables in Unity Catalog, handles incremental ingestion, maps data types.

FastTrack: Provides enum translation, sub-table resolution, view syntax replacement, and entity list templates — directly addresses documented Silver-layer pain points.

AI: Generates cleansing, SCD merge logic, DQ expectations, business-key resolution scaffolding per entity.

## 6.3 Effort Breakdown

| Activity | Unit count | Hrs / unit | Total hrs |
| --- | --- | --- | --- |
| Discovery: AX 2012 → D365 F&O entity mapping; SQL view analysis (AI-assisted) | 200 entities + 500 SQL views | ~2.5 | 500–600 |
| Raw layer framework (mostly eliminated by connector) | 1 framework | — | 40–60 |
| Raw layer per-entity (connector configuration + verification) | 200 entities | ~1 | 150–200 |
| Silver layer framework (FastTrack pattern port to Databricks) | 1 framework | — | 150–200 |
| Silver layer per-entity implementation (AI-generated, FastTrack-informed) | 200 entities | ~4 | 700–900 |
| Data-quality validation & reconciliation vs. AX 2012 / Synapse Link source | 200 entities | 2 | 400 |
| Documentation (AI-generated) | — | — | 50 |
| Phase 2 Total |  |  | 1,990–2,410 |

Person-days: 284–344 · Person-months: 13–16 · Effort reduction vs baseline: 58–66%

## 6.4 Retained Databricks-Specific Considerations

- Lakeflow Connect connector: 250 tables/pipeline limit still applies; domain-oriented pipelines required

- Connector does not support automated schema evolution — schema-drift monitoring capability still required

- F&O virtual entities (mserp_ prefix) — FastTrack pattern (remove_mserp_prefix) applies

- Option sets ingest as integer codes; lookups as GUIDs — FastTrack enum translation pattern used in Silver

- Multi-select option sets ingest as comma-separated strings — Silver-layer parsing required

- Synapse Link export latency 5–15 minutes — not real-time (unchanged from baseline)

# 7. Phase 3 — Dimensional Model (Gold Layer)

## 7.1 Scope

- Design an enterprise Kimball-style dimensional model spanning all in-scope business domains

- Define conformed dimensions used across multiple facts (Date, Customer, Vendor, Product, Legal Entity, etc.)

- Define fact tables at explicit grain, with clearly documented measures and business rules

- Implement dimension and fact tables in Delta Lake with surrogate keys, referential integrity, and SCD Type 1/2 where appropriate

- Validate business rules and perform reconciliation against Silver layer sources and AX 2012 legacy reports

## 7.2 Where the Accelerators Apply

FastTrack: F&O CDM metadata encodes entity relationships and primary/foreign keys. Financial dimensions framework knowledge (up to ~50 dimensions, DimensionAttributeValueSet structure). Entity Store aggregate measurement patterns (LedgerActivityMeasure, BudgetActivityMeasure) provide reference patterns for Finance/GL dimensional models.

AI: Dim/fact DDL generation, ELT pipeline scaffolding, surrogate key logic, SCD merge scripts, referential integrity checks, unit test stubs, documentation.

D365 Connector: Marginal — cleaner Bronze/Silver output means less investigation of raw table structure by modellers.

## 7.3 Effort Breakdown

| Activity | Unit count | Hrs / unit | Total hrs |
| --- | --- | --- | --- |
| Enterprise dimensional model design: bus matrix, domain workshops, conformed dimensions, grain definitions | ~10 domains | 65–70 | 650–700 |
| Dimension table implementation (AI-generated scaffolding) | 50 dims | 11–12 | 550–600 |
| Fact table implementation (AI-generated scaffolding, senior review) | 30 facts | 20–22 | 600–650 |
| Cross-cutting: surrogate key framework, referential integrity checks, late-arriving dimensions | 1 framework | — | 280 |
| Validation & reconciliation across all Gold tables | 80 tables | ~4 | 300 |
| Documentation and lineage capture in Unity Catalog (AI-generated) | — | — | 70 |
| Phase 3 Total |  |  | 2,450–2,600 |

Person-days: 350–371 · Person-months: 16–17 · Effort reduction vs baseline: 30–34%

# 8. Phase 4 — One Big Table (OBT)

## 8.1 Scope

- Design analytically-oriented denormalized wide tables per business domain, driven by insight consumption patterns

- Build OBTs using the Dimensional Model as source, with joined dimension attributes and pre-computed measures

- Apply Databricks-specific optimization: liquid clustering, Photon-optimized layouts, incremental MERGE refresh, and Delta caching

- Validate business rules and data consistency against the underlying dimensional model

## 8.2 Where the Accelerators Apply

AI: OBT column suggestion from questionnaire pattern analysis, join scaffolding, incremental MERGE generation, Databricks Workflow orchestration, liquid clustering key suggestion, reconciliation SQL templates, documentation.

FastTrack and D365 Connector: Marginal — indirect benefit through cleaner dimensional model in Phase 3.

## 8.3 Effort Breakdown

| Activity | Unit count | Hrs / unit | Total hrs |
| --- | --- | --- | --- |
| OBT design: identify required OBTs, define grain, dimensions/facts to include, calculated columns | 30 OBTs | ~7 | 220 |
| OBT implementation: join logic, denormalization, pre-aggregation, incremental refresh, orchestration (AI-scaffolded) | 30 OBTs | 18 | 540 |
| Performance optimization: partitioning, liquid clustering, Photon, caching, query profiling | 30 OBTs | ~4 | 130 |
| Validation: business rule verification, completeness, reconciliation to Dimensional Model | 30 OBTs | 6 | 180 |
| Documentation and Unity Catalog metadata (AI-generated) | — | — | 50 |
| Phase 4 Total |  |  | 1,120 |

Person-days: 160 · Person-months: 7 · Effort reduction vs baseline: 35%

Critical constraint: Phase 4 has the highest downstream consequence per hour of any phase. An OBT error propagates to hundreds of Phase 5 insights simultaneously. Senior review is retained despite AI leverage.

# 9. Phase 5 — Business Insight Implementation

## 9.1 Scope

- Implement ~12,000 business insights against the OBT layer, driven by the approved questionnaire responses

- Develop reusable calculation patterns, transformation templates, and testing scaffolding before scaling the team

- Validate every implemented insight against its documented requirement

- Support UAT with business users; log, prioritize, and resolve UAT feedback

## 9.2 Where the Accelerators Apply

AI (dominant contribution): - Simple insights (40% of 12,000): near-deterministic questionnaire → SQL mapping; engineer reviews and validates. Throughput 10–15 insights/engineer/day. - Medium insights (40%): AI generates base structure and standard date logic templates; engineer adjusts. Throughput 5–7/day. - Complex insights (20%): AI generates boilerplate; senior engineer leads. Throughput 2–3/day. - Auto-generated unit tests from questionnaire expected behaviour - Auto-generated traceability documentation

FastTrack: Marginal — where dimensional model was FastTrack-informed, insight code hits cleanly-structured OBTs.

D365 Connector: No direct contribution at insight layer.

## 9.3 Complexity Distribution and Effort

| Complexity | Share | Count | Baseline hrs | With AI |
| --- | --- | --- | --- | --- |
| Simple: single aggregation, basic filter, standard KPI | 40% | 4,800 | 3,000 | 1,200–1,400 |
| Medium: multi-step calculation, conditional logic, period comparisons | 40% | 4,800 | 7,200 | 4,300–4,600 |
| Complex: cross-functional, multi-currency, complex business rules, variance analysis | 20% | 2,400 | 7,200 | 5,400–5,600 |
| Raw development subtotal | 100% | 12,000 | 17,400 | 10,900–11,600 |

## 9.4 Full Phase 5 Effort

| Component | Hours |
| --- | --- |
| Raw development subtotal (AI-assisted) | 10,900–11,600 |
| Reuse & batching efficiency (~25% reduction; compounds with AI) | (4,350) |
| Adjusted development effort | 6,550–7,250 |
| Unit testing & validation (avg. ~9 min per insight with AI-generated tests) | 1,700–1,800 |
| UAT preparation | 600 |
| UAT support & issue resolution (~15% of insights need discussion) | 1,500–1,600 |
| Rework from UAT feedback (~10% rework rate) | 900–950 |
| Documentation & traceability (AI-generated) | 200 |
| AI agent priming (new activity) | 200–400 |
| Phase 5 Total | 11,650–12,800 |

Person-days: 1,664–1,829 · Person-months: 77–84 · Effort reduction vs baseline: 38–43%

Throughput Requirement: 12,000 insights delivered across ~5 months of active development requires an average team throughput of approximately 130 insights per working day. With AI-assisted development at ~7–8 insights/engineer/day (blended average across complexity tiers), this implies ~17–19 people focused on Phase 5 development for the duration — down from 30+ in baseline.

# 10. Total Effort Summary

| Phase / Component | Hours | Person-days | Person-months |
| --- | --- | --- | --- |
| Phase 1 — Business Insight Review (6 weeks) | 6,300–6,700 | 900–957 | 41–44 |
| Phase 2 — Raw & Silver | 1,990–2,410 | 284–344 | 13–16 |
| Phase 3 — Dimensional Model (Gold) | 2,450–2,600 | 350–371 | 16–17 |
| Phase 4 — One Big Table | 1,120 | 160 | 7 |
| Phase 5 — Insight Implementation | 11,650–12,800 | 1,664–1,829 | 77–84 |
| Cross-cutting roles (SA, PM, SM, BA overlap) | 3,000 | 429 | 20 |
| Contingency (10%) | 2,651–2,863 | 379–409 | 17–19 |
| Grand Total | ~29,200–31,500 | ~4,170–4,500 | ~192–207 |

## 10.1 Scenario Sensitivity

Three scenarios reflecting different accelerator effectiveness levels:

| Scenario | Basis | Total effort | Peak team | Avg team |
| --- | --- | --- | --- | --- |
| Optimistic | High questionnaire quality; high AI priming quality; strong FastTrack pattern reuse; standard F&O deployment | ~26,000 hrs | 27 | 21 |
| Realistic (baseline) | Moderate questionnaire quality; adequate AI priming; typical FastTrack applicability; some client customisations | ~29,200–31,500 hrs | 29–32 | 22 |
| Conservative | Questionnaire quality issues; weak AI priming; heavy client F&O customisation outside FastTrack templates | ~40,000 hrs | 40 | 30 |

The conservative scenario approaches but does not reach the baseline (~47,000 hrs) because the D365 connector still eliminates most Bronze work regardless of other accelerator effectiveness.

# 11. Team Composition by Phase

## 11.1 Phase 1 Team

| Role | Count | Responsibilities |
| --- | --- | --- |
| Data Engineer (Reviewer) | 30–32 | AI-assisted questionnaire review, ambiguity resolution, business-user discussions |
| Business Analyst | 2 | Business-user coordination, review-progress tracking |
| D365 F&O Functional Consultant | 1 | ERP-domain support |
| Project Manager | 1 | Delivery coordination |
| Solution Architect (part-time) | 1 | Consistency oversight |
| Phase 1 subtotal | ~35–37 |  |

## 11.2 Phase 2 Team

| Role | Count | Responsibilities |
| --- | --- | --- |
| Data Architect | 2 | Silver-layer architecture, FastTrack pattern porting, DQ framework |
| Senior Data Engineer (Databricks) | 2 | Framework code, connector configuration, review of AI-generated code |
| Data Engineer (Databricks) | 2–3 | AI-assisted per-entity Silver implementation |
| D365 F&O Functional Consultant | 1–2 | Entity mapping for client-specific customisations |
| QA / Data Tester | 2 | Reconciliation, DQ validation |
| Business Analyst | 2 | Requirements clarification, SQL view analysis |
| Phase 2 subtotal | 11–13 |  |

## 11.3 Phase 3 Team

| Role | Count | Responsibilities |
| --- | --- | --- |
| Data Architect / Data Modeller | 3 | Enterprise model design, bus matrix, conformed dimensions |
| Senior Data Engineer (Databricks) | 2 | Fact pipeline review, SCD logic verification |
| Data Engineer (Databricks) | 3–4 | AI-generated dim/fact implementation |
| D365 F&O Functional Consultant | 1 | Business rule interpretation |
| QA / Data Tester | 2 | Reconciliation, business rule testing |
| Business Analyst | 2 | Domain workshops, design validation |
| Phase 3 subtotal | 13–14 |  |

## 11.4 Phase 4 Team

| Role | Count | Responsibilities |
| --- | --- | --- |
| Data Architect | 1 | OBT design, optimization strategy |
| Senior Data Engineer (Databricks) | 2 | OBT construction, performance tuning |
| Data Engineer (Databricks) | 3 | AI-scaffolded OBT implementation |
| QA / Data Tester | 1–2 | Validation, reconciliation |
| Phase 4 subtotal | 7–8 |  |

## 11.5 Phase 5 Team

| Role | Count | Responsibilities |
| --- | --- | --- |
| Senior Data Engineer | 4 | Complex insight logic, AI-generated code review, mentoring |
| Data Engineer | 10–12 | AI-assisted insight development at scale |
| Business Analyst | 3 | Requirement interpretation, business user liaison, UAT coordination |
| QA / Data Tester | 3 | Insight validation, UAT support |
| D365 F&O Functional Consultant | 2 | Business rule clarification during implementation |
| Phase 5 subtotal | 22–24 |  |

## 11.6 Cross-Cutting (Full Duration)

| Role | Count | Duration |
| --- | --- | --- |
| Solution Architect | 2 | Months 1–9 |
| Project Manager | 2 | Months 1–9 |
| Scrum Master / Delivery Lead | 1 | Months 1–9 |

# 12. Phase Dependencies, Parallelism, and Schedule

## 12.1 Dependency Chain (Unchanged)

Phase 1 must complete before Phase 2 begins. Within Phases 2–5, significant overlap is possible.

- Phase 1 → Phase 2: All 12,000 questionnaires must be reviewed, clarified, and marked ready. Phase 1 runs Weeks 1–6.

- Phase 2 → Phase 3: Once the first cohort of Silver tables is validated (~Month 2), dimensional modeling for that domain can start.

- Phase 3 → Phase 4: Once dimensions and facts for a domain are complete, OBT construction begins. Phase 4 begins Month 4.

- Phase 4 → Phase 5: Once the first OBTs are validated, insight implementation begins. Phase 5 begins Month 5.

- Phase 5 UAT: Runs in waves starting Month 6, final UAT completing Month 9.

## 12.2 Schedule Overview

Phase 1 runs across Weeks 1–6; Phases 2–5 run across Months 1–9 of the implementation program.

| Phase | W1 | W2 | W3 | W4 | W5 | W6 | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Phase 1 — Insight Review | ◐ | ● | ● | ● | ● | ◐ |  |  |  |  |  |  |  |  |  |
| Phase 2 — Raw & Silver |  |  |  |  |  |  | ● | ● | ● | ◐ |  |  |  |  |  |
| Phase 3 — Dimensional Model |  |  |  |  |  |  |  | ◐ | ● | ● | ◐ |  |  |  |  |
| Phase 4 — OBT |  |  |  |  |  |  |  |  |  | ◐ | ● | ◐ |  |  |  |
| Phase 5 — Insight Development |  |  |  |  |  |  |  |  |  |  | ◐ | ● | ● | ● | ◐ |
| Phase 5 — UAT |  |  |  |  |  |  |  |  |  |  |  | ◐ | ● | ● | ● |

● = full activity; ◐ = ramping up or winding down; (blank) = not active

## 12.3 Key Milestones

| Milestone | Target |
| --- | --- |
| Phase 1 kickoff; reviewer team onboarded | Week 1 |
| 50% of questionnaires reviewed | End of Week 3 |
| 100% of questionnaires marked ready for technical analysis | End of Week 6 |
| Phase 2 kickoff; D365 connector configured; discovery spike complete | End of Month 1 |
| FastTrack pattern port to Databricks complete | Month 2 |
| Raw layer live for all entities (connector-driven) | Month 2 |
| Silver layer complete for all entities | Month 4 |
| Enterprise dimensional model design approved | Month 3 |
| All dimension and fact tables loaded and validated | Month 5 |
| All OBTs built and validated | Month 6 |
| AI agent priming complete | End of Month 4 |
| 50% of business insights implemented | Month 7 |
| 100% of business insights implemented | Month 8 |
| UAT complete, sign-off obtained | Month 9 |

# 13. Resource Ramp-Up and Ramp-Down Plan

## 13.1 Phase 1 Staffing (Weeks 1–6)

| Role | W1 | W2 | W3 | W4 | W5 | W6 |
| --- | --- | --- | --- | --- | --- | --- |
| Data Engineer (Reviewer) | 18 | 32 | 32 | 32 | 32 | 18 |
| Business Analyst | 2 | 2 | 2 | 2 | 2 | 2 |
| D365 F&O Functional Consultant | 1 | 1 | 1 | 1 | 1 | 1 |
| Project Manager | 1 | 1 | 1 | 1 | 1 | 1 |
| Solution Architect (part-time) | 1 | 1 | 1 | 1 | 1 | 1 |
| Weekly total | 23 | 37 | 37 | 37 | 37 | 23 |

## 13.2 Phases 2–5 Staffing (Months 1–9)

| Role | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Solution Architect | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 |
| Project Manager | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |
| Scrum Master / Delivery Lead | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |
| Data Architect / Modeller | 2 | 3 | 3 | 2 | 1 | 1 | 1 | — | — |
| Senior Data Engineer (Databricks) | 3 | 3 | 3 | 4 | 5 | 5 | 4 | 3 | 2 |
| Data Engineer (Databricks) | 3 | 5 | 6 | 8 | 11 | 12 | 12 | 9 | 5 |
| D365 F&O Functional Consultant | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | — |
| Business Analyst | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 2 |
| QA / Data Tester | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 2 |
| Monthly total | 18 | 22 | 23 | 26 | 29 | 31 | 29 | 22 | 15 |

## 13.3 Ramp Profile Narrative

- Weeks 1–6 (Phase 1) — Dedicated review cohort of ~35–37 people, half capacity in W1 and W6. Weekly throughput target: ~2,000 questionnaires reviewed per week.

- Transition (end of W6) — Strongest 8–10 reviewers convert to Phase 2/3 seniors and BAs. Remaining reviewers demobilize.

- Months 1–2 — Ramp-up. D365 connector configuration, FastTrack pattern port, AI framework setup. Discovery spike.

- Months 3–4 — Build-up. Silver layer completes across entities. Phase 3 dimensional-model build accelerates. AI agent priming in preparation for Phase 5.

- Months 5–7 — Peak. Phase 5 insight implementation drives peak staffing at 29–31 people. Assembly-line AI-assisted development.

- Months 8–9 — Ramp-down. UAT support, defect resolution, stabilization. Progressive team release.

# 14. Risks, Assumptions, Constraints, and Bottlenecks

## 14.1 Assumptions

- The 12,000 completed insight questionnaires are of sufficient quality to serve as functional requirements

- D365 F&O is operational; Synapse Link replication (managed by another team) is available by Month 1

- Azure Databricks workspace, ADLS Gen2 storage, Unity Catalog metastore, and networking are provisioned before project start

- Business users are available for design workshops, clarification calls, and UAT

- No significant changes to D365 F&O configuration or business processes during the 9-month window

- The AI agent can be primed with F&O domain context, dimensional model, OBT schemas, and questionnaires

- Client F&O deployment is close enough to standard that FastTrack templates apply meaningfully

## 14.2 Risk Register

| Risk | Impact | Likelihood | Mitigation |
| --- | --- | --- | --- |
| Insight questionnaires are incomplete or ambiguous at scale | Phase 5 AI leverage collapses; effort +30–50%; timeline at risk | Medium–High | Sample 100 questionnaires in Month 1; build rework buffer; escalate quality issues before Phase 5 scaling |
| AI agent priming quality is inadequate | Phase 5 throughput below expected; extra rework | Medium | Dedicate senior engineers to priming in Months 3–4; validate on pilot 200-500 insights before Phase 5 scales |
| Client-specific F&O customisations fall outside FastTrack templates | Phase 2 Silver effort +20–40% | Medium | Engage D365 F&O functional consultants early; validate FastTrack pattern applicability in discovery spike |
| D365 F&O data model differences from AX 2012 larger than expected | Phase 2 entity-mapping effort up to 2× for affected domains | Medium | Engage D365 F&O functional consultants early; use Microsoft’s AX-to-D365 mapping documentation |
| Synapse Link replication delays or gaps | Blocks Phase 2 start; may require full refreshes | Medium | Clear SLA with replication team; monitor Synapse Link health; establish alerting |
| Lakeflow Connect connector limitations (250 tables/pipeline, no auto schema evolution) | Additional pipeline management overhead | High (already known) | Design multiple domain-oriented pipelines; build schema-drift monitoring |
| Business user availability for UAT | Phase 5 UAT extends beyond Month 9 | Medium–High | Secure named UAT participants and scheduled time blocks before project start |
| Onboarding 30+ resources creates coordination overhead | Productivity loss of 15–25% in first 2 weeks per cohort | Medium | Stagger onboarding in 3 waves; prepare onboarding packs, coding standards, and environment access in advance |
| AI-generated code contains subtle correctness errors | UAT rework rate higher than 10% assumed | Medium | Preserve senior engineer review; mandatory validation against expected output before UAT |
| Complex insight share is higher than assumed 20% | Phase 5 effort +15–25% | Medium | Sample complexity distribution in Phase 1; adjust staffing by end of Month 5 if trending |

## 14.3 Constraints

- The 9-month timeline is fixed. The primary lever available to management is team size, not duration.

- Power BI report and dashboard redesign is explicitly out of scope

- All work is on the Azure Databricks platform

- AI agent must be domain-primed before Phase 5 begins — this is a non-negotiable prerequisite for the projected Phase 5 throughput

## 14.4 Primary Bottlenecks

- Phase 5 throughput — 12,000 insights in ~5 months demands AI-assisted assembly-line discipline. AI priming and pattern templates must be established in Months 4–5 before the full Phase 5 team scales.

- D365 F&O functional knowledge for client customisations — Only 2 functional consultants planned. If client customisations create bottleneck, increase to 3.

- QA capacity during UAT — Parallel UAT streams across domains require coordinated test execution. AI-generated test cases help but human sign-off is essential.

# 15. Final Recommendation

## 15.1 Recommended Team Composition at Peak

| Role | Peak | Key skills |
| --- | --- | --- |
| Solution Architect | 2 | Azure data platform, Databricks, dimensional modeling, D365 F&O data model, AI agent integration |
| Project Manager | 2 | Large-scale data program delivery, hybrid/agile methodology |
| Scrum Master / Delivery Lead | 1 | Agile delivery, team coordination, impediment removal |
| Data Architect / Data Modeller | 2 | Enterprise dimensional modeling (Kimball), Databricks/Delta Lake |
| Senior Data Engineer (Databricks) | 5 | PySpark/Spark SQL, Delta Lake, ELT pipeline design, AI code review, complex transformations |
| Data Engineer (Databricks) | 11 | PySpark/Spark SQL, Delta Lake, AI-assisted pipeline development |
| D365 F&O Functional Consultant | 2 | AX 2012 and D365 F&O data model, entity mapping, ERP business processes |
| Business Analyst | 3 | Requirements analysis, ERP business processes, UAT coordination |
| QA / Data Tester | 3 | Data reconciliation, automated testing, UAT management |
| Total at peak | 31 |  |
| Average over 9 months | 22 |  |

## 15.2 Critical Success Factors

- Validate questionnaire quality early. Sample 100 questionnaires in Week 1. If more than 30% need significant rework, the AI leverage assumption is invalidated and Phase 5 staffing must revert toward baseline.

- Prime the AI agent thoroughly before Phase 5. Feed the F&O entity model, dimensional model, OBT schemas, and approved questionnaires into the AI agent. Validate on 200–500 pilot insights before scaling.

- Configure the D365 connector correctly on day one. Domain-oriented pipeline design (respecting 250-tables-per-pipeline limit) must be right the first time. Test against a representative subset in the discovery spike.

- Port FastTrack patterns to Databricks early. The Silver-layer framework port must complete in Month 2 before per-entity implementation ramps.

- Track velocity weekly. Insights completed per engineer per day is the single most important metric. If actual throughput is below 5 insights/engineer/day in Phase 5, escalate staffing within two weeks.

- Secure business-user commitment contractually. UAT will not succeed if domain experts are only “available when they can be.” Named participants with blocked calendar time are essential.

- Preserve senior seats. AI leverage does not scale down the sign-off responsibility. Every OBT, every dimensional model, every insight ultimately requires human confirmation of correctness.

- Stagger onboarding. Bringing 30+ people onto the project simultaneously will collapse productivity. Onboard in 3 waves: core team (Month 1), Phase 3/4 additions (Month 3), Phase 5 scaling (Month 5).

- Reserve human capacity for client-specific F&O customisations. These fall outside FastTrack templates and can consume disproportionate effort if under-resourced.

## 15.3 Bottom Line

The v3.0 realistic scenario requires ~192–207 person-months of effort delivered by a team averaging 22 FTEs and peaking at 29–32 FTEs across 9 months, on Azure Databricks with the Lakeflow Connect D365 connector consuming Synapse Link output from ADLS Gen2, using FastTrack patterns in the Silver layer and AI-assisted development throughout. Delivery is feasible with the plan above.

The two variables most likely to determine whether the 9-month timeline holds are Phase 1 questionnaire quality (the upstream gate for Phase 5 AI leverage) and AI agent priming quality (the enabler of Phase 5 throughput). Business-user availability during UAT is a secondary but material risk.

# Appendix A — Basis of Estimate

These estimates apply three accelerators to the v2.0 baseline: an AI development agent, the Microsoft FastTrack Implementation Assets, and the Azure Databricks Lakeflow Connect D365 connector. A 10% contingency has been applied to the grand total.

## Assumed Productivity Baseline

- 7 productive hours per person per day

- ~21.7 working days per month; ~195 working days across 9 months

- ~1,365 productive hours per person over the 9-month program

- ~152 productive hours per person per month

## Accelerator Assumptions

- AI agent priming completed in Months 3–4 (200–400 hrs), primed with F&O entity model, Phase 3 dimensional model, Phase 4 OBT schemas, and approved Phase 1 questionnaires

- FastTrack patterns ported to Databricks in Month 2 — enum translation, sub-table resolution, mserp_ prefix handling, view syntax replacement

- D365 connector operational from Month 1 — Bronze layer streaming tables auto-generated from Synapse Link output in ADLS Gen2

- AI-assisted throughput: simple insights 10–15/engineer/day, medium insights 5–7/day, complex insights 2–3/day; blended ~7–8/day

## Recalibration Triggers

- Entity count > 240 or < 160 after discovery

- More than 30% of sampled insight questionnaires require rework

- Fewer than 5 insights per engineer per day during first 2 weeks of Phase 5

- Synapse Link availability < 95% during Phase 2

- Business-user availability for design workshops falls below 0.5 FTE per domain

- AI-generated Silver code failing DQ checks above 20% baseline rate

- Client F&O customisations require more than 30% of Phase 2 effort outside FastTrack templates

# Appendix B — Version History

v2.0 (baseline) — Original estimate. ~47,036 hrs, 45 peak FTEs, 10.5 months. Assumed green-field Databricks build without AI or accelerator support.

v3.0 (this document) — Accelerator-adjusted estimate applying: - Azure Databricks Lakeflow Connect D365 connector (Bronze layer automation) - Microsoft FastTrack Implementation Assets (Silver layer patterns) - AI development agent (code generation across Phases 2–5)

Result: ~29,200–31,500 hrs, 29–32 peak FTEs, 10.5 months (unchanged timeline). ~33–38% effort reduction, ~29–36% peak headcount reduction.

Arithmetic verified: All phase totals sum from activity breakdowns. Grand total sums from phase totals plus 10% contingency. Recommended peak team composition sum = 31 (verified by row addition).