## Slide 1
ENTERPRISE PROGRAM PROPOSAL
D365 F&O Analytics
Migration Delivery Plan
Resource, effort & schedule estimate — accelerator-adjusted for Phases 1 through 5
PLATFORM & ACCELERATORS
Azure Databricks · ADLS Gen2 · Unity Catalog · Delta Lake · Lakeflow Connect D365 · FastTrack · AI Agent
TIMELINE
6 weeks (Phase 1) + 9 months (Phases 2–5) · ~10.5 months total
v3.0
July 2026

## Slide 2
01 · EXECUTIVE SUMMARY
The program at a glance
Migrating from AX 2012 to D365 F&O analytics on Azure Databricks, using the medallion architecture with three accelerators applied: the Databricks D365 connector for Bronze automation, Microsoft FastTrack patterns for Silver, and an AI agent for code generation across Phases 2–5. Delivers 12,000 business insights in a fixed 9-month window.
~30k
Total person-hours
range 29.2k–31.5k · v2 was 47k
~200
Person-months
range 192–207 · v2 was 310
28
Peak team size
range 26–29 · v2 was 45
10.5
Total months
timeline unchanged from v2
THE DOMINANT WORKSTREAM
Phase 5 — Business Insight Implementation
Represents ~40% of accelerator-adjusted program effort (11,650–12,800 hours). Delivery of 12,000 insights over ~5 months of active development requires ~130 insights/day — now achievable with 9–11 data engineers (down from 20) via AI-assisted pattern-based development. Phase 1 (upstream) sets the input quality for AI leverage; questionnaire quality is the gate.
D365 F&O Analytics Migration · Resource Estimate v3.0
2 / 15

## Slide 3
02 · SOLUTION ARCHITECTURE
Databricks medallion with accelerators
SOURCE
F&O Source
D365 F&O Source
Managed by separate team
Synapse Link exports F&O data to ADLS Gen2 (CDM changelog format)
PHASE 2A · ACCELERATED
Raw Layer
Bronze / Raw Layer
Databricks D365 Connector
Auto-discovers schema, creates streaming tables, handles CDC. Eliminates most Bronze engineering.
PHASE 2B
Silver Layer
Silver Layer
FastTrack patterns + AI code gen
Enum decode, GUID resolve, dedup, SCD, DQ — ported from FastTrack CDMUtil to Databricks
PHASE 3
Dimensional Model
Gold — Dimensional Model
Enterprise Kimball star schema
~50 dimensions · ~30 facts · surrogate keys · SCD 1/2 · liquid clustering — AI-scaffolded
PHASE 4
Big Tables
Gold — One Big Tables
Denormalized analytical layer
~30 OBTs · Photon-optimized · incremental MERGE · AI join scaffolding
PHASE 5
Insight Layer
Insight Layer
12,000 business insights
AI-generated SQL/PySpark, Phase 1 questionnaires as spec. Consumed by Power BI (out of scope).
GOVERNANCE & ACCELERATORS
Unity Catalog
Central governance, lineage, column-level security
Delta Live Tables + Workflows
Orchestration with retries, alerting, lineage capture
FastTrack CDM patterns
Enum, sub-table, view-syntax, mserp_ prefix handling
AI Development Agent
Code gen: DDL, PySpark, SCD, DQ, tests, docs
Databricks Asset Bundles + Azure DevOps
CI/CD across all layers
Custom Schema-Drift Monitoring
Connector does not auto-evolve schema
D365 F&O Analytics Migration · Resource Estimate v3.0
3 / 15

## Slide 4
03 · SCOPE BASELINE
What we are building (unchanged from v2)
200
D365 F&O entities to ingest
GL · AP · AR · FA · Inventory · Procurement · Sales · Production · Budget · HR
50
Dimension tables (Gold)
Customer · Vendor · Item · Account · Date · Legal Entity · Cost Center · Site · Warehouse · Worker · +
30
Fact tables (Gold)
GL journal · AP · AR · POs · SOs · inventory · production · budget · fixed assets · +
30
One Big Tables
One primary OBT per analytical domain, plus supporting variants for specialized workloads
12,000
Business insights
750 reports × 4 pages × 4 insights per page. Documented via 24-question questionnaires (already reviewed).
10
Business domains
Finance · AP · AR · FA · Inventory · Procurement · Sales · Production · HR · Cross-functional
Recommended action: 2-week discovery spike in Weeks 1–2 to validate these counts before final staffing commitments.
D365 F&O Analytics Migration · Resource Estimate v3.0
4 / 15

## Slide 5
04 · PHASE 1
Business Insight Review — 6-week precursor
PHASE 1 EFFORT
6,300–6,700
person-hours
900–957
Person-days
41–44
Person-months
30–32
Engineer-reviewers required
Weeks 1–6 (pre-implementation)
Scope
Read and understand each business insight in its report context
Validate all 24 responses per questionnaire for completeness and clarity
Identify missing, ambiguous, or conflicting information
Schedule and conduct clarification discussions with business users
Update questionnaires and mark ready for technical analysis (Phase 2)
ESTIMATION MODEL (REALISTIC, AI-ASSISTED)
Base review time (with AI duplicate & completeness check)
25 min per insight questionnaire
Discussion rate
22% of insights require a business-user discussion
Discussion duration
30 min per discussion (avg. incl. scheduling & write-up)
Effective time / insight
31.6 min → 12,000 × 31.6 min = 6,300–6,700 hours total
D365 F&O Analytics Migration · Resource Estimate v3.0
5 / 15

## Slide 6
05 · PHASE 2
Raw & Silver — ingestion and standardization
PHASE 2 EFFORT
1,990–2,410
person-hours
58–66%
effort reduction vs baseline
284–344
Person-days
13–16
Person-months
11–13
Team size at phase peak
Months 1–4
Scope
Configure D365 connector against ADLS Gen2 (Synapse Link output)
Discover entities via AX 2012 SQL view analysis (AI-assisted)
Bronze layer: auto-created streaming tables by Lakeflow Connect connector
Silver layer: cleansing, decoding, SCD, DQ — FastTrack patterns + AI code gen
Validate row counts and business-key reconciliation vs. AX 2012 source
ACCELERATOR IMPACT — WHERE THE SAVINGS COME FROM
D365 Connector
Auto-creates Bronze streaming tables from ADLS Gen2 — eliminates ~250 hrs of custom ingestion
FastTrack patterns
Enum decode, sub-table, mserp_ prefix, view syntax — ported to Databricks in Silver framework
AI code generation
Per-entity Silver transformations, SCD merge, DQ rules — from ~10 hrs/entity to ~4 hrs/entity
Retained work
250-tables-per-pipeline limit; schema-drift monitoring; option-set decoding still required
D365 F&O Analytics Migration · Resource Estimate v3.0
6 / 15

## Slide 7
06 · PHASE 3
Dimensional Model — the enterprise Gold layer
PHASE 3 EFFORT
2,450–2,600
person-hours
30–34%
effort reduction vs baseline
350–371
Person-days
16–17
Person-months
13–14
Team size at phase peak
Months 2–5
Key deliverables
10
Business domains modelled
Bus matrix, conformed dimensions, grain definitions per domain
50
Dimensions
SCD Type 1 & 2, surrogate keys, conformed across facts — AI-generated scaffolding
30
Facts
Explicit grain, defined measures, business rules verified — senior review
APPROACH
Kimball methodology
Enterprise bus matrix drives conformed dimensions across domains
FastTrack-informed
F&O CDM metadata + Entity Store aggregate patterns accelerate design
AI-generated scaffolding
Dim/fact DDL, SCD merge logic, unit tests, referential integrity checks
Iterative by domain
Domain-oriented waves overlap with Phase 2 tail (starting Month 2)
D365 F&O Analytics Migration · Resource Estimate v3.0
7 / 15

## Slide 8
07 · PHASE 4
One Big Tables — analytics-optimized denormalization
PHASE 4 EFFORT
1,120
person-hours
35%
effort reduction vs baseline
160
Person-days
7
Person-months
7–8
Team size at phase peak
Months 4–6
Building the consumption layer
~30 OBTs denormalize the Gold dimensional model into wide analytical tables. One primary OBT per business domain plus supporting variants. AI-scaffolded, senior-reviewed — a Phase 4 error propagates to hundreds of Phase 5 insights.
Design
Grain, dim/fact selection, calculated columns
220 hrs
Implementation
Join logic, denormalization, MERGE refresh — AI-scaffolded
540 hrs
Optimization
Liquid clustering, Photon, caching
130 hrs
Validation
Business rule verification, reconciliation
180 hrs
Documentation
Unity Catalog metadata, lineage
50 hrs
D365 F&O Analytics Migration · Resource Estimate v3.0
8 / 15

## Slide 9
08 · PHASE 5 · DOMINANT WORKSTREAM
Business Insight Implementation
PHASE 5 EFFORT
11,650–12,800
person-hours
~40%
of total program effort
~130 / day
Required insight throughput
~7–8 / eng-day
Blended throughput (AI-assisted)
Months 5–9
Complexity mix across 12,000 insights — 38–43% reduction with AI
Chart: 
| Simple (40%) | Medium (40%) | Complex (20%)
Baseline hrs | 3000 | 7200 | 7200
With AI (hrs) | 1300 | 4450 | 5500
EFFORT BREAKDOWN
Adjusted development (with AI + 25% reuse)
6,550–7,250 hrs
Unit testing & validation (AI-generated tests)
1,700–1,800 hrs
UAT support & rework
2,400–2,550 hrs
Preparation, docs & AI agent priming
1,000–1,200 hrs
D365 F&O Analytics Migration · Resource Estimate v3.0
9 / 15

## Slide 10
09 · TOTAL EFFORT
Phase totals and scenario sensitivity (v3)
Effort by phase (person-hours)
Chart: 
| Phase 1 | Phase 2 | Phase 3 | Phase 4 | Phase 5 | Cross-cutting | Contingency
Baseline v2 | 7500 | 5800 | 3700 | 1710 | 20550 | 3500 | 4276
With Accelerators v3 | 6500 | 2200 | 2525 | 1120 | 12225 | 3000 | 2757
Scenario planning (v3)
OPTIMISTIC
26,000 hrs
27 peak
21 avg
High questionnaire quality; high AI priming; strong FastTrack fit; standard F&O
REALISTIC · RECOMMENDED
29,200–31,500 hrs
29–32 peak
22 avg
Moderate questionnaire quality; adequate AI priming; typical FastTrack fit
CONSERVATIVE
40,000 hrs
40 peak
30 avg
Questionnaire issues; weak AI priming; heavy client customisation outside FastTrack
D365 F&O Analytics Migration · Resource Estimate v3.0
10 / 15

## Slide 11
10 · TEAM COMPOSITION
Roles and headcount at peak (28 FTEs, v3)
Chart: 
| Solution/Data Architect | D365 F&O Consultant | Project Manager | Business Analyst | QA / Data Tester | Senior Data Engineer | Data Engineer
Peak headcount | 2 | 2 | 2 | 3 | 3 | 5 | 11
22
DELIVERY CORE
Engineers, testers, and BAs building the platform and insights
2
ARCHITECTURE
Solution and data architects setting patterns and standards
2
MANAGEMENT
Program leadership and delivery coordination
2
SPECIALISTS
D365 F&O functional consultants bridging AX-to-D365 knowledge
D365 F&O Analytics Migration · Resource Estimate v3.0
11 / 15

## Slide 12
11 · SCHEDULE
Phase 1 (6 weeks) then Phases 2–5 (9 months)
Wk 1–6
M1
M2
M3
M4
M5
M6
M7
M8
M9
Phase 1 — Insight Review
Phase 2 — Raw & Silver
Phase 3 — Dimensional Model
Phase 4 — OBT
Phase 5 — Insight Dev
Phase 5 — UAT
KEY MILESTONES
W6
Phase 1 complete · questionnaires ready
M1
D365 connector configured · discovery spike done
M2
FastTrack patterns ported · Bronze live
M4
AI agent primed · Silver complete
M5
Dim & Fact tables loaded
M7
50% of insights implemented
M9
UAT complete · sign-off
D365 F&O Analytics Migration · Resource Estimate v3.0
12 / 15

## Slide 13
12 · RAMP PROFILE
Monthly headcount — full program (Phase 1 + Phases 2–5)
Chart: 
| W1 | W2 | W3 | W4 | W5 | W6 | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9
Without AI (Baseline v2) | 23 | 37 | 37 | 37 | 37 | 23 | 23 | 28 | 31 | 35 | 43 | 45 | 42 | 35 | 21
With AI + FastTrack (v3) | 20 | 32 | 32 | 32 | 32 | 20 | 18 | 22 | 23 | 26 | 27 | 29 | 27 | 20 | 13
W1–W6
RAMP-UP
Phase 1: Insight review. 32–37 reviewers peak. AI duplicate detection + summarisation.
M1–M2
BUILD-UP
Core team onboards. D365 connector + FastTrack Silver framework. AI agent priming begins.
M3–M6
PEAK
Phase 5 peak: 27–29 FTEs. AI-assisted assembly-line insight implementation at scale.
M7–M9
RAMP-DOWN
UAT support and defect resolution. Progressive team release.
D365 F&O Analytics Migration · Resource Estimate v3.0
13 / 15

## Slide 14
13 · RISKS
Top program risks and mitigations (v3)
HIGH
Questionnaire quality below expectation
Impact: AI leverage collapses · Phase 5 effort +30–50%
Sample 100 questionnaires in Week 1; build rework buffer; escalate before Phase 5 scaling
HIGH
AI agent priming inadequate
Impact: Phase 5 throughput below target · extra rework
Dedicate seniors to priming Months 3–4; pilot on 200–500 insights before scaling
MEDIUM
Client-specific F&O customisations outside FastTrack
Impact: Phase 2 Silver effort +20–40% for affected domains
Engage functional consultants early; validate FastTrack fit in 2-week discovery spike
MEDIUM
Onboarding drag from scaling
Impact: 15–25% productivity loss per onboarding cohort
Stagger onboarding in 3 waves; onboarding packs, standards, and environment ready in advance
MEDIUM
AI-generated code contains subtle errors
Impact: UAT rework rate higher than 10% assumed
Preserve senior engineer review; mandatory validation against expected output before UAT
MEDIUM
Business user availability for UAT
Impact: UAT extends beyond Month 9
Secure named UAT participants with blocked calendar time before project start
D365 F&O Analytics Migration · Resource Estimate v3.0
14 / 15

## Slide 15
14 · RECOMMENDATION
Bottom line & next steps
The 9-month timeline is feasible with a team averaging 22 FTEs and peaking at 26–29 FTEs on Azure Databricks, using the Lakeflow Connect D365 connector, FastTrack patterns, and AI-assisted development. Effort drops ~33–38% vs the v2 baseline. Phase 1 questionnaire quality and AI agent priming quality are the two variables most likely to determine whether the savings materialise.
CRITICAL SUCCESS FACTORS
01
Validate questionnaire quality in Week 1
Sample 100 questionnaires. If >30% need rework, revert to baseline staffing.
02
Prime the AI agent thoroughly
F&O model, dim model, OBT schemas, questionnaires. Pilot on 200–500 insights first.
03
Configure D365 connector on day one
Domain-oriented pipeline design (250 tables/pipeline) must be right the first time.
04
Port FastTrack patterns early
Silver framework port must complete Month 2 before per-entity implementation ramps.
05
Preserve senior seats
AI leverage does not scale down the sign-off responsibility.
06
Track velocity weekly
Insights per engineer per day. Adjust staffing by Month 5 if <5/day.
D365 F&O Analytics Migration · Resource Estimate v3.0
15 / 15